## Tasks
META FUNCTIONALITY | Notes | Est (days) | Need Date
Remote Server - Dymola/Creo/NRMM |  | 2 | Nov 8th
Limits --- waiting on meta change? | Needed for all TestBenches |  | Nov 8th
PET - TB CAD to Modelica flow; Modelica to CAD flow | Needed for: Cg to aqatic flow; ride height |  | Nov 8th
MultiFidelity (from TestBench) | Needed to hedge modelica model risk |  | Nov 8th
Design Traversal | Count seats, take max of all lead times |  | Nov 8th
Test Injection Points | Needed for scalability (NRMM params from components) |  | Dec 1st
PCC - what is left here? | Necessary for FANG, ideally run on JPL server farm |  | Nov 8th
TestBench Compliance Tool (ensure no TB modifications, MD5) | Necessary for FANG |  | Dec 1st
Master Master T
Battery of TestBenches | New language element, ref to all testbenches, ordering?? | 2 | Nov 8th
TestBench Export/Import | Needed for CyDesign |  | Dec 1st
Component Export/Import | Necessary for FANG |  | Nov 8th
Design DDP Export/Import | Necessary for FANG |  | Nov 8th
VF Integration (component, TB, Design interchange) | Necessary for FANG |  | Nov 8th
BOM Output | Necessary for FANG |  | Nov 22th
TDP/Design Submit: Draw out CAD assy/STEP export/DDP export=> ZIP MFG Extract |  |  | Nov 22th
** need to work out & draw out the process for this
DESIGN SPACE - what is left?
CAD - what is left?
Cyber (no FANG dependency)
Scoring - what is left?
Interference Check - not needed for FANG-1
Ricardo's Three:
BOM OUTPUT - Score design completeness. Nut to bolt level, but will need hydrolic fittings. Anything not there you have to give reasoning.
CAD /CyPhy Interface Check - check all interface connections made
Fastener and other Self-Certify - on VF?
VM's
AVM VM's
eucatools
Get more dedicated nodes (4 cores for now, 20k later)

## Nov PI Mtg
Attendees: | Day 1 |  | Day 2 |  | Day 3
Sandeep | 9am-10am | Component Model Integration | 8:30am - 11am | SSP | 8am-12pm | FANG Challenge 2 Deep Dive
Ted |  | Adam, Blane, Sandeep |  | Ted, Sandeep, Xenofon |  | Everyone minus Adam and Zsolt
Justin |  |  | 9am - 10am | VF/FANG
Jason | 10am-11am | Context & TestBench |  | Justin, Jason
Adam |  | Jason, Ted, Sandeep | 10am-11am | VF/C2M2L
Zsolt |  |  |  | Adam, Jason, Justin
Xenofon | 11am-12pm | Mfg Model Demo | 11am-12pm | VF/iFAB
|  | audience.. |  | Adam
| 1pm-2pm | VF/META | 1pm-3pm | Modelica
|  | Jason-TB |  | Zsolt, Sandeep, Fritz, Ted, Jason
|  | Justin FANG-Beta | 3pm-4pm | Beta Test - MasterBetas Present
|  | Zsolt-Dymola |  | Bernie, Julie, Justin (+Ted/Jason)
|  | Ted, Sandeep | 4pm-5pm | Road to FANG 1 Challenge
|  | Adam - DDP, etc. |  | PCC on AMES, …
Justin, Ted, Jason, …
| 2pm-3pm | iFAB/META
TDP-Join
CAD output
Mfg Query
todo: need to work the TDP export process
Adam, Zsolt, Ted, Sandeep, Justin