## Sheet1
META FUNCTIONALITY | Status | Availability | Beta Testing Date | First FANG Target Use | Tool Release Date | C2M2L Model Support | Notes
Design Space Representation and Navigation
Capability: Representation & Processing of Large Design Spaces
Specification of Design Spaces | Proto | Now | 2012-09-01 | FANG 1 | 2012-01-01 | N/A
Scalable Design Space Reduction | Proto | Now | 2012-09-01 | FANG 1 | 2012-01-01 | N/A
Synthesis of Design Points from Constrained Design Spaces | Proto | Now | 2012-09-01 | FANG 1 | 2012-01-01 | N/A
Dynamics Analysis (Across Design Spaces)
Capability: Rapid Composition of Dynamics Analysis at Multiple Abstractions
Specification of Dynamics Tests (Scenario, Environment, Metrics, Limits) | Proto | Now | 2012-09-01 | FANG 1 | 2012-01-01 | Yes
Composition of Modelica Simulations | Proto | Now | 2012-09-01 | FANG 1 | 2012-01-01 | Yes
Execution in Dymola / OpenModelica | Proto | Now | 2012-09-01 | FANG 1 | 2012-01-01 | Yes/Partial
Postprocessing of Metrics and Limit Checking | Proto | Now | 2012-09-01 | FANG 1 | 2012-01-01 | In Devel
Multi-Fidelity Simulation | In Devel | 2012-11-15 | 2012-11-15 | FANG 1 | 2012-01-01 | In Devel
Accuracy Estimation | 2013 | 2013-07-01 |  | FANG 2 | 2013-07-01 | Yes
Limited Open Source Support | In Devel | 2012-11-15 | 2012-11-15 | FANG 1 | 2012-01-01 | In Devel
Full Open Source Support | 2013 | 2013 |  | FANG 2 | 2013-07-01 | 2013 | OpenModelica + Modelon + Model Simplification
CAD/Geometric Design (Across Design Spaces)
Capability: Rapid Composition of 3D Models for Production and Analysis
CAD Interface and Join Specification | Proto | Now | 2012-09-01 | FANG 1 | 2012-01-01 | TBD
CAD Assembly From Models | Proto | Now | 2012-11-07 | FANG 1 | 2012-01-01
Manufacturing TDP Gen | Spec/Devel | 2012-11-15 | 2012-11-15 | FANG 1 | 2012-01-01
Interface Detail Elaboration | 2013 | 2013 | 2013-07-01 | FANG 2 | 2012-01-01
Wiring Harness Design | 2013 | 2013 | 2013-07-01 | FANG 2 | 2012-01-01
Seals/Weld Design | 2013 | 2013 | 2013-07-01 | FANG 2
CAD Interoperability | ??? | ??? | ??? | ??? | ??? |  | No Source Identified Yet (IntentSoft Tasks Orthogonal)
Finite Element Analysis (Across Design Spaces)
Capability: Rapid Composition of Structural and Thermal Analysis
Specification of Structural Tests (Env, Boundary Conditions, Forcing Functions) | Proto | Now | 2013-07-01 | FANG 2 | 2012-01-01 | TBD | Could be applied selectively in FANG 1 or by Fang Performer
Specification of Thermal Tests (BC, Therm Sources) | In Devel | Now | 2013-07-01 | FANG 2 | 2012-01-01
Composition of FEA (Grid, NASTRAN Deck Creation) | Proto | Now | 2013-07-01 | FANG 2 | 2012-01-01
Execution in Abaqus/Calculix | Proto | Now | 2013-07-01 | FANG 2 | 2012-01-01
PostProcessing of Metrics and Quality Check | In Devel | 2012-12-01 | 2013-07-01 | FANG 2 | 2012-01-01
Visualization Tools
Capability: Understanding of Design Spaces and Design Analysis Results
Dashboard | Curr Vers = 0.61 | Now | 2012-09-01 | Nov 8th | 2012-01-01 | Yes | Beta Testing
Raw Data Visualizer | Prototype | 2012-11-15 | 2012-11-15 | Nov 15th | 2012-01-01 | Yes | Re-configured from a web-based to a local application
Complexity Analysis (Across Design Spaces)
Capability: Prediction of Design Risk/Success/Cost
Structural Complexity Analysis Tool | Proto | 2012-11-01 | 2012-11-15 | FANG 1 | 2012-01-01 | Yes | Needs Calibration (MIT+VU+Ricardo Sessions Needed)
Entropy-Based Complexity Analysis | Proto | 2012-11-01 | 2012-11-15 | FANG 1 | 2012-01-01 | Yes | Couples with PCC Tool
PCC
Capability: Certification of Requirements Over Component Variations
Simulation-Based PCC (Open Source) | Proto | Now | 2012-11-01 | FANG 1 | 2012-01-01 | Yes | Dependent on OSS OpenModelica
Simulation Based PCC (Dassault) | In Devel | 2012-11-01 | 2012-11-15 | FANG 1 | 2012-01-01 | Yes | Integration Efforts Ongoing, DS Devel Dependencies
Parametric Exploration Tools
Parametric Exploration (DOE) with OpenMDAO | Proto | Now | 2012-11-01 | FANG 1 | 2012-01-01 |  | Considering Suspension Design Application Use in FANG 1
Parametric Optimization with OpenMDAO | Proto | Now | 2012-01-01 | FANG 2 | 2012-01-01
Computational Fluid Dynamics
Capability: Rapid Composition of Fluid Properties
Specification of Fluid Tests (Env, Boundary Conditions, Forcing Functions) | 2013 |  | 2013-07-01 | FANG-2 | 2013-07-01 | C2M2L-2
Composition of CFD (Grid, OpenFOAM Deck Creation) | 2013 |  | 2013-07-01 | FANG-2 | 2013-07-01 | C2M2L-2 | Note: OpenFOAM being used by BAE for Hull Aquatic Resistance
Execution in OpenFOAM | 2013 |  | 2013-07-01 | FANG-2 | 2013-07-01 | C2M2L-2
PostProcessing of Metrics and Quality Check | 2013 |  | 2013-07-01 | FANG-2 | 2013-07-01 | C2M2L-2
Cyber-Physical System Tools
Capability: Integrated Design and Analysis of Software & System Dynamics
Specification of Controllers (State & Signal Flow) | Now | 2012-11-01 | 2012-11-01 | FANG-1 | 2012-01-01 | C2M2L-2
Generation of Implementation | Proto |  |  | FANG-1 | 2012-01-01 | C2M2L-2
CoSimulation with Dynamics | Proto |  |  | FANG-1 | 2012-01-01 | C2M2L-2
Survivability Analysis
Capability: Composition of Survivability Analysis for Blast & Penetration
Specification of Penetration Tests (Env, Boundary Conditions, Forcing Functions) | Design | Now | 2013-07-01 | FANG 2 | 2012-01-01 | TBD | Could be applied selectively in FANG 1 or by Fang Performer
Specification ofBlast Tests (BC, Sources) | Design | Now | 2013-07-01 | FANG 2 | 2012-01-01
Composition of Simulations | 2013 | Now | 2013-07-01 | FANG 2 | 2012-01-01
Execution in SWRI Tools | 2013 | Now | 2013-07-01 | FANG 2 | 2012-01-01
PostProcessing of Metrics and Quality Check | 2013 | 2012-12-01 | 2013-07-01 | FANG 2 | 2012-01-01
Mobility Analysis/Evaluation
Capability: Composition of 3D Mobility Analysis and Vehicle Simulation
Specification of Design Mobility Elements | Devel | 2013-01-01 | 2013-07-01 | FANG 2 | 2012-01-01 | C2M2L-2
Generation of Implementation | Design | 2013-04-01 | 2013-07-01 | FANG 2 | 2012-01-01 | C2M2L-2
CoSimulation with Dynamics | Design | 2013-04-01 | 2013-07-01 | FANG 2 | 2012-01-01 | C2M2L-2
Verification
Capability: Composition of Reliability, FME Analysis, State Space Exploration
Reliability Analysis | 2013 | 2013-01-01 | 2013-07-01 | FANG 2 | 2012-01-01 | C2M2L-2
FME Analysis | 2013 | 2013-04-01 | 2013-07-01 | FANG 2 | 2012-01-01 | C2M2L-2
QR | 2013 | 2013-04-01 | 2013-07-01 | FANG 2 | 2012-01-01 | C2M2L-2
RA
FANG Execution Tools
Capability: Produce iFAB-Production-Ready Designs
TestBench Compliance Tool (ensure no TB modifications, MD5) | Design | Dec 1st |  | FANG 1 |  |  | Necessary for FANG Performer
Completeness Checking | Defining Concept | Dec 15th |  | FANG 1 |  |  | Need Definition of "Completeness"
BOM Output | Design | Nov 22th |  | FANG 1 |  |  | Necessary for FANG
Services
Capability: Remote Services to Support FANG Users Without COT$ Tools
Remote Execution Server - Dymola | Proto | 2012-11-08 | 2012-11-08 | FANG-1 | 2012-01-01
Remote Execution Server - Creo | Devel | 2012-11-15 | 2012-11-15 | FANG-1 | 2012-01-01
Remote Execution Server - NRMM | Devel | 2012-11-22 | 2012-11-22 | FANG-1 | 2012-01-01